## Template
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Girishkumar
Gowtham
Mani Maran
Mohammed Irfan
Ponvizhi
Pooja
Ranjith
Sandhiya
Sriram
Venkateshwaran

## 05.04.2022
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Venkateshwaran | Individual Admin and Reviewer Flow | Created User stories for individual actors |  | 6 | 1
Mani Maran | Individual Admin and Reviewer Flow | Created User stories for individual actors |  | 6 | 1
Ponvizhi | Individual Query Solver and Query Raiser | Created User stories for individual actors |  | 6 | 1
Mohammed Irfan | Individual Query Solver and Query Raiser | Created User stories for individual actors |  | 6 | 1
Sandhiya | Creation of User Flow,Admin flow | Created User stories for individual actors |  | 6 | 1
Pooja | Creation of User Flow,Admin flow | Created User stories for individual actors |  | 6 | 1
Ranjith | Absent | Created User stories for individual actors | Absent | Absent | Absent
Sriram | Absent | Created User stories for individual actors | Absent | Absent | Absent
Gowtham | Absent | Created User stories for individual actors | Absent | Absent | Absent
Girishkumar | Creation of User Flow,Admin flow | Created User stories for individual actors |  | 6 | 1

## 06.04.2022
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Girishkumar | Refining of Admin flow,and started with creating wireframe for forum | Created admin flow and refined the user stories |  | 6 | 1
Gowtham | Discuss about user flow and create user flow diagram.create wire frame for admin side -reviewer &user verification view. | Absent |  | 5 | 1
Mani Maran | Refining of Individual Admin flow and Reviewer flow,refined in Actor flow docs and started with creating wireframe for Admin Dashboard page. | Created Individual admin and Reviewer flow,Added MOM in excel |  | 5 | 2
Mohammed Irfan | Refining of Query solving and Query Raising flow.Created Wireframe for Reviewing page. | Created User stories for individual actors,Added Query raiser and query solver in excel. |  | 5 | 2
Ponvizhi | Refining User Flow of Query solving and Query Raising .Created Wireframe for Reviewer Dashboard. | Created User stories for individual actors,Added Query raiser and query solver in excel. |  | 5.5 | 1
Pooja | Refined the User flow according to the suggestions given and wireframe for articless . | Created User Flow,User stories for Article publisher and reader has been refined |  | 6 | 1
Ranjith | Absent | Absent | Absent | Absent | Absent
Sandhiya | Creation of Reviewer flow and started creating wireframe for home page,profile page ,article page. | Created User flow and admin flow and refined user stories for author |  | 6 | 1
Sriram | Refining the queryraiser and query solver.Created wireframework for login and register | Absent |  | 6 | 1
Venkateshwaran | Refining of the reviewer flow,Started Creating the wireframe for spam query report and user authorization | Created Individual user flow and refined with the user stories |  | 5 | 2

## 07.04.2022
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Girishkumar | Created Wireframes for forum page,query raising page,report query page and view query page. | Refined the Admin flow and started planning wireframes for forum |  | 6 | 1
Gowtham | created wire frame for admin side -reviewer &user verification view. | Discuss about user flow and create user flow diagram.Planning wire frame for admin side -reviewer &user verification view.
Mani Maran | Created Wireframe for Admin Dashboard overview page,Employees page . | I wrote Acceptance Criteria,Dependencies,constraints for Article reviewer |  | 2,1.5,1.5,1 | 2
Mohammed Irfan | Created wireframe for Reviewer page,publish and report page. | Refined query solver,query raiser flow and discuss with team about wireframe. |  | 6 | 1
Ponvizhi | Created wireframe for Reviewer Dashboard.Acceptance criteria for Query Solver. | Refining query solver , query raiser and created wireframe for reviewer dashboard. |  | 6 | 1.5
Pooja | The wireframe for Myarticles,Published articles and Draft has been created | The User flow has been refined and the wireframe for Myarticles has been planned |  | 7 | 1
Ranjith
Sandhiya | Created HomePage,Profile and article page | Refined Review flow and started with planning Wireframe for Home ,Profile and article page. |  | 6 | 1.5
Sriram | Creating Login and Register page. Acceptance criteria for Query Raiser | Refined query raiser flow and started planning wireframe for Login,Register page. |  | 6 | 1
Venkateshwaran | Created wrieframe for spamreports | I have created acceptance criteria , dependencies,constraints for Admin |  | 1.5,1.5,1.5,1 | 3