## Sheet1
S.No | Task | Sub Tasks | Estimation in Hrs | Code Merging
1 | User Home Page | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 2 | Compatibility testing
|  | HTML Validations | 1.5 | Deployment Documentation
|  | Web API Integration | 2
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1.5
|  | Code Review | 1
|  | Unit Testing | 2
|  | Total Time | 19
Code Merging
2 | Spam Report(Admin) | Low Level Design - Sequence Diagram | 5 | Integration Testing
|  | HTML preparation | 5.5 | Compatibility testing
|  | HTML Validations | 2 | Deployment Documentation
|  | Web API - Service Implementation i).GetQueriesByVerifyStatus -2hrs ii).GetSpamCountForQueryID -1.5hrs iii).DeleteSpamsByQueryID -1.75hrs iv).RemoveQueryByQueryID -1.75hrs v).ApproveSpam -1.5hrs vi).RejectSpam -1.5hrs | 10
|  | Web API Integration | 2
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging i).GetQueriesByVerifyStatus -1hr ii).GetSpamCountForQueryID -1hr iii).DeleteSpamsByQueryID -1hr iv).RemoveQueryByQueryID -1hr v).ApproveSpam -1hr vi).RejectSpam -1hr | 6
|  | Code Cleanup | 1
|  | Code Review | 0.5
|  | Unit Testing i).GetQueriesByVerifyStatus -0.5hr ii).GetSpamCountForQueryID -0.5hr iii).DeleteSpamsByQueryID -0.75hr iv).RemoveQueryByQueryID -0.75hr v).ApproveSpam -0.5hr vi).RejectSpam -0.5hr | 3.5
|  | Total Time | 37.5
3 | Admin Dashboard | Low Level Design - Sequence Diagram | 3 | Integration Testing
|  | HTML preparation | 4 | Compatibility testing
|  | HTML Validations | 0.5 | Deployment Documentation
|  | Web API - Service Implementation i).GetArticles -2hrs ii).GetUsers -2hrs iii).Getusers(isreviewer) -2hrs iv).GetQueries(issolved) -2hrs | 8
|  | Web API Integration | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging i).GetArticles -1hr ii).GetUsers -1hr iii).Getusers(isreviewer) -1.5hr iv).GetQueries(issolved) -1.5hr | 5
|  | Code Cleanup | 1
|  | Code Review | 0.5
|  | Unit Testing i).GetArticles - 0.75hr ii).GetUsers -0.75hr iii).Getusers(isreviewer) -0.75hr iv).GetQueries(issolved) -0.75hr | 3
|  | Total Time | 30
4 | Specific Query | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 5 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
|  | Web API Integration | 2
Web API - Service Implementation
|  | Create Query | 2
|  | GetQueryById | 1
|  | AddCommentToQuery | 3
|  | GetComments | 1
|  | MarkQueryAsSolved | 2
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 4
|  | Code Cleanup | 0.5
|  | Code Review | 1
|  | Unit Testing | 2
|  | Total Time | 28.5
5 | Raise Query | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 4 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
|  | Web API Integration | 2
|  | Web API - Service Implementation | 5
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
|  | Total Time | 20
6 | Report Spam(User) | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 5 | Compatibility testing
|  | HTML Validations | 2 | Deployment Documentation
Web API - Service Implementation
|  | 1.ReportSpam | 3
|  | Web API Integration | 5
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 4
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 4
|  | Total Time | 28
7 | My Profile | Low Level Design - Sequence Diagram | 1 | Integration Testing
|  | HTML preparation | 4 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
|  | Web API Integration | 1
|  | Web API - Service Implementation | 4
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 1
|  | Unit Testing | 1
|  | Total Time | 16.5
8 | Login | Low Level Design - Sequence Diagram | 1 | Integration Testing
|  | HTML preparation | 3 | Compatibility testing
|  | HTML Validations | 3 | Deployment Documentation
|  | Web API Integration | 3
|  | Web API - Service Implementation | 5
|  | Swagger - API Documentation | 3
|  | Service Validations , Exception and Logging | 4
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Total Time | 25
9 | Register Page | Low Level Design - Sequence Diagram | 1 | Integration Testing
|  | HTML preparation | 2 | Compatibility testing
|  | HTML Validations | 6 | Deployment Documentation
|  | Web API Integration | 4
|  | Web API - Service Implementation | 7
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 4
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Total Time | 28
10 | Specific Article View | Low Level Design - Sequence Diagram | 3 | Integration Testing
|  | HTML preparation | 3 | Compatibility testing
|  | HTML Validations | 3 | Deployment Documentation
|  | Web API Integration | 4
Web API - Service Implementation
|  | 1.Get Article by ID | 3
|  | 2.add comment to article | 3
|  | 3.Get comments | 2
|  | 4. Add like to artice | 4
|  | 5.Get like count | 2
|  | Swagger - API Documentation | 4
|  | Service Validations , Exception and Logging | 4
|  | Code Cleanup | 1
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Total Time | 38.5
11 | User Verification | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 4 | Compatibility testing
|  | HTML Validations | 2 | Deployment Documentation
Web API Service Implementation
|  | 1.getUser | 2
|  | 2.changeverificationstatus | 2
|  | Web API - Integration | 4
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 4
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Total Time | 25
12 | Employees | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 4 | Compatibility testing
|  | HTML Validations | 2 | Deployment Documentation
Web API Service Implementation
|  | 1.getusers | 2
|  | 2.disableuser | 2
|  | 3.markasreviewer | 2
|  | 4.getreviewer | 2
|  | Web API - Integration | 4
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 4
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Total Time | 29
13 | Particular Article Review | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 3 | Compatibility testing
|  | HTML Validations | 2 | Deployment Documentation
Web API - Service Implementation
|  | 1.UpdateArticleStatus | 3
|  | Web API Integration | 4
|  | Swagger - API Documentation | 3
|  | Service Validations , Exception and Logging | 3
|  | Code Cleanup | 1
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Total Time | 23.5
14 | To Review | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 4 | Compatibility testing
|  | HTML Validations | 2 | Deployment Documentation
Web API - Service Implementation
|  | 1.GetArticles | 2
|  | 2.GetArticleById | 1
|  | Web API Integration | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 3
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Total Time | 22
15 | Reviewer Dashboard | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 3 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
Web API - Service Implementation
|  | 1.GetArticlesByVerifyStatus | 2
|  | Web API Integration | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Total Time | 18
16 | Article Reviewed | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 3 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
Web API - Service Implementation
|  | 1.GetArticles | 1
|  | 2.GetArticleById | 1
|  | Web API Integration | 3
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 3
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Total Time | 18
17 | Latest Articles | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 3 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
|  | Web API - Service Implementation | 5
|  | Web API Integration | 4
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 4
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2.5
|  | Total Time | 24.5
18 | Trending Articles | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 3 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
|  | Web API - Service Implementation | 5
|  | Web API Integration | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 3
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Total Time | 22
19 | Latest Queries | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 3 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
|  | Web API - Service Implementation | 4
|  | Web API Integration | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 3
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Total Time | 21
20 | Trending Queries | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 3 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
|  | Web API - Service Implementation | 4
|  | Web API Integration | 3
|  | Swagger - API Documentation | 3
|  | Service Validations , Exception and Logging | 4
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Total Time | 23
21 | Articles | Low Level Design - Sequence Diagram | 3 | Integration Testing
|  | HTML preparation | 4 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
Web API - Service Implementation
|  | 1.Get Articles() | 5
|  | 2.Get ArticlesByAuthor() | 2
|  | 3.Get ArticlesByTitle() | 2
|  | 4.Get ArticlesBy DateRange() | 2
|  | Web API Integration | 3
|  | Service Validations , Exception and Logging | 5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 3
|  | Total Time | 31
22 | Queries | Low Level Design - Sequence Diagram | 3 | Integration Testing
|  | HTML preparation | 4 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
Web API - Service Implementation
|  | Get Queries() | 5
|  | Get Queries(IsSolved) | 2
|  | Get QueriesByTitle() | 3
|  | Web API Integration | 4
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 3
|  | Total Time | 33
23 | My Articles | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 3 | Compatibility testing
|  | HTML Validations | 2 | Deployment Documentation
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
|  | Total Time | 19
24 | My Queries | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 3 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
|  | Web API Integration | 2
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
|  | Total Time | 19
25 | Create Article | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 5 | Compatibility testing
|  | HTML Validations | 3 | Deployment Documentation
Web API - Service Implementation
|  | 1.Create Article | 5
|  | Web API Integration | 4
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 4
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Total Time | 28
26 | Update Article | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 4 | Compatibility testing
|  | HTML Validations | 2 | Deployment Documentation
Web API - Service Implementation
|  | 1.Update Article | 3
|  | Web API Integration | 4
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 4
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Total Time | 24
27 | Specific Query View | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 3 | Compatibility testing
|  | HTML Validations | 0.5 | Deployment Documentation
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 2
|  | Code Review | 2
|  | Unit Testing | 2
|  | Total Time | 19.5
28 | Rejection page for article | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 1
Web API - Service Implementation
|  | 1.SendNotification | 2
|  | Web API Integration | 2
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 2
|  | Code Review | 2
|  | Unit Testing | 2
|  | Total Time | 19
|  | TOTAL HOURS | 689.5