## Template
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Girishkumar
Gowtham
Mani Maran
Mohammed Irfan
Ponvizhi
Pooja
Ranjith
Sandhiya
Sriram
Venkateshwaran

## 05.04.2022
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Venkateshwaran | Individual Admin and Reviewer Flow | Created User stories for individual actors |  | 6 | 1
Mani Maran | Individual Admin and Reviewer Flow | Created User stories for individual actors |  | 6 | 1
Ponvizhi | Individual Query Solver and Query Raiser | Created User stories for individual actors |  | 6 | 1
Mohammed Irfan | Individual Query Solver and Query Raiser | Created User stories for individual actors |  | 6 | 1
Sandhiya | Creation of User Flow,Admin flow | Created User stories for individual actors |  | 6 | 1
Pooja | Creation of User Flow,Admin flow | Created User stories for individual actors |  | 6 | 1
Ranjith | Absent | Created User stories for individual actors | Absent | Absent | Absent
Sriram | Absent | Created User stories for individual actors | Absent | Absent | Absent
Gowtham | Absent | Created User stories for individual actors | Absent | Absent | Absent
Girishkumar | Creation of User Flow,Admin flow | Created User stories for individual actors |  | 6 | 1

## 06.04.2022
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Girishkumar | Refining of Admin flow,and started with creating wireframe for forum | Created admin flow and refined the user stories |  | 6 | 1
Gowtham | Discuss about user flow and create user flow diagram.create wire frame for admin side -reviewer &user verification view. | Absent |  | 5 | 1
Mani Maran | Refining of Individual Admin flow and Reviewer flow,refined in Actor flow docs and started with creating wireframe for Admin Dashboard page. | Created Individual admin and Reviewer flow,Added MOM in excel |  | 5 | 2
Mohammed Irfan | Refining of Query solving and Query Raising flow.Created Wireframe for Reviewing page. | Created User stories for individual actors,Added Query raiser and query solver in excel. |  | 5 | 2
Ponvizhi | Refining User Flow of Query solving and Query Raising .Created Wireframe for Reviewer Dashboard. | Created User stories for individual actors,Added Query raiser and query solver in excel. |  | 5.5 | 1
Pooja | Refined the User flow according to the suggestions given and wireframe for articless . | Created User Flow,User stories for Article publisher and reader has been refined |  | 6 | 1
Ranjith | Absent | Absent | Absent | Absent | Absent
Sandhiya | Creation of Reviewer flow and started creating wireframe for home page,profile page ,article page. | Created User flow and admin flow and refined user stories for author |  | 6 | 1
Sriram | Refining the queryraiser and query solver.Created wireframework for login and register | Absent |  | 6 | 1
Venkateshwaran | Refining of the reviewer flow,Started Creating the wireframe for spam query report and user authorization | Created Individual user flow and refined with the user stories |  | 5 | 2

## 07.04.2022
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Girishkumar | Created Wireframes for forum page,query raising page,report query page and view query page. | Refined the Admin flow and started planning wireframes for forum |  | 6 | 1
Gowtham | created wire frame for admin side -reviewer &user verification view. | Discuss about user flow and create user flow diagram.Planning wire frame for admin side -reviewer &user verification view.
Mani Maran | Created Wireframe for Admin Dashboard overview page,Employees page . | I wrote Acceptance Criteria,Dependencies,constraints for Article reviewer |  | 2,1.5,1.5,1 | 2
Mohammed Irfan | Created wireframe for Reviewer page,publish and report page. | Refined query solver,query raiser flow and discuss with team about wireframe. |  | 6 | 1
Ponvizhi | Created wireframe for Reviewer Dashboard.Acceptance criteria for Query Solver. | Refining query solver , query raiser and created wireframe for reviewer dashboard. |  | 6 | 1.5
Pooja | The wireframe for Myarticles,Published articles and Draft has been created | The User flow has been refined and the wireframe for Myarticles has been planned |  | 7 | 1
Ranjith
Sandhiya | Created HomePage,Profile and article page | Refined Review flow and started with planning Wireframe for Home ,Profile and article page. |  | 6 | 1.5
Sriram | Creating Login and Register page. Acceptance criteria for Query Raiser | Refined query raiser flow and started planning wireframe for Login,Register page. |  | 6 | 1
Venkateshwaran | Created wrieframe for spamreports | I have created acceptance criteria , dependencies,constraints for Admin |  | 1.5,1.5,1.5,1 | 3

## 08.04.2022
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Girishkumar | Refined the wireframes of forum module like adding query page,Viewing specific query page and commenting to the query and search query | Created wireframes for forum pages like query viewing,adding quering,reporting spam |  | 6 | 2
Gowtham | Refined the wireframes of admin page and created entity model | created wire frame for admin side -reviewer &user verification view. |  | 5 | 1
Mani Maran
Mohammed Irfan | Work on entity model on Reviewer Dashboard. | Redefined Wireframe for Reviewer Dashboard,Publish and Reject Page. |  | 6 | 2
Ponvizhi |  | Created wireframe for Reviewer Dashboard |  | 6 | 2
Pooja | Refined the WireFrames for Published Articles,Draft and Worked on entity model | Created the wireframes for My Articles page,Published and Draft page and Create Articles Page |  | 3,1,1 | 2
Ranjith
Sandhiya | Refined the wireframe for homepage, article page and added pagenation and worked on entity model | Created wireframe for homepage and article page |  | 6 | 1.5
Sriram | Refined the wieframe for Login and register page and worked on entity model on query raiser | Created wireframe for login and register |  | 6 | 2
Venkateshwaran | Working on entity model | Refined the wireframe Spam query list and reported query list |  | 1,1,1 | 2,1,1,1,1

## 09.04.2022
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Girishkumar
Gowtham | Refining Admin page and worked on entity model | created wire frame for admin side -reviewer &user verification view
Mani Maran
Mohammed Irfan | Work on entity model. | Refined the wireframe for Reviewer dashboard,Review page and Publish page |  | 6 | 1
Ponvizhi
Pooja | Refined The Wireframes based on the suggestions given, and Worked on Entity Models | Refined the WireFrames for Published Articles,Draft and Worked on entity model |  | 2,1.5,2 | 1
Ranjith
Sandhiya | Refined the wireframe for homepage,articlepage and worked on entity models | Refined the wireframe for homepage,profile page and article page |  | 6 | 1
Sriram | Refined made on login and register wireframe and worked on entity model on query | Changes made on entity model and wireframe |  | 6 | 1
Venkateshwaran | Worked on Entity Models and Refining the wireframes | Refined wireframes on spam report list |  | 2,2,1 | 2

## 11.04.2022
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Girishkumar | Refined the Wireframes of Forum pages Like Adding query pageand viewing query page,Discussed about the data model entities and created the data model | Made the changes in the forum wireframe |  | 6 | Explored on data model and DBcontext -1
Gowtham
Mani Maran | 1.Refining Admin Dashboard Wireframe. 2.Discussing about Entity Data Model. 3.Started designing Data model | Completed Changes in Wireframe. Explored about Middlewares and Pipelines |  | 2 1 2 | 1.5
Mohammed Irfan | Refined Reviwer Dashboard,Reviewer page,Publish page and Discussed the data models. | Refined the Changes in Wireframe(Reviewer flow). |  | 5 | 1
Ponvizhi | Refined Reviewer Dashboard and Dissued Data Models and created data models | Refined the changes in reviewer dashboard |  | 5 | 1
Pooja | Refined the Wireframes of Articles Page, Created MOM, Discussed the Data Models and created data models | Refined the changes in the Articles and forum Page.Explored on EAR |  | 5 | 1
Ranjith
Sandhiya | Refined Article Page ,Created Data Model with example | Refined Changes in Home Page,discussed and created DataModel |  | 5 | 1
Sriram
Venkateshwaran