## Sheet1
Work Items | Completed | In Progress | Yet to start
Low Level Design | *LLD Work is Completed | *Working on the Design approach | null
Web API Implementation | *Completed all API | *Refining the Code using sonarQube analysis | null
Angular Component Creation | * All Components has been created | *Working on the responsiveness | null
Web API and Angular Integration | *Completed all integration | null | null
Web API Testing | *Writing test cases is completed TOTAL =320 PASSED=306,FAILED =14 | Working on the Failed test cases | null
Linting | *Linting work is completed | null | null
SonarQube | *Static analysis for the web api is completed | Refining the code with stats | null
Swagger Documentation | *Completed the Swagger Documentation | null | null
Load Testing(Jmeter) | null | *Working on the Load testing of the app | null
Angular component testing | null | *Working on angular component testing | null
Deployement | null | *Refering about the deployement in AWS | Yet to Start deployment
Documentation | null | null | Yet To start