## Sheet1
S.No | Task | Sub Tasks | Estimation in Hrs | Code Merging
1 | User Home Page | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 3 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
|  | Web API Integration | 2
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Integration Testing | 1
|  | Total Time | 19
Code Merging
2 | Spam Report(Admin) | Low Level Design - Sequence Diagram | 4 | Integration Testing
|  | HTML preparation | 2 | Compatibility testing
|  | HTML Validations | 0.5 | Deployment Documentation
|  | Web API Integration | 4
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 3
|  | Code Cleanup | 1
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Integration Testing | 1
|  | Total Time | 23
3 | Admin Dashboard | Low Level Design - Sequence Diagram | 3 | Integration Testing
|  | HTML preparation | 4 | Compatibility testing
|  | HTML Validations | 0.5 | Deployment Documentation
|  | Web API Integration | 4
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 3
|  | Code Cleanup | 1
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Integration Testing | 0.5
|  | Total Time | 23.5
4 | Specific Query | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 4 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
|  | Web API Integration | 3
|  | Web API - Service Implementation | 5
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Integration Testing | 1
|  | Total Time | 23
5 | Raise Query | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 3 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
|  | Web API Integration | 1.5
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Integration Testing | 2
|  | Total Time | 18.5
6 | Report Spam(User) | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 3 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
|  | Web API Integration | 2
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Integration Testing | 1
|  | Total Time | 18
7 | My Profile | Low Level Design - Sequence Diagram | 1 | Integration Testing
|  | HTML preparation | 3 | Compatibility testing
|  | HTML Validations | 0.5 | Deployment Documentation
|  | Web API Integration | 1
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
|  | Integration Testing | 1
|  | Total Time | 13.5
8 | Login | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 3 | Compatibility testing
|  | HTML Validations | 2 | Deployment Documentation
|  | Web API Integration | 2
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Integration Testing | 1
|  | Total Time | 19
9 | Register Page | Low Level Design - Sequence Diagram | 1 | Integration Testing
|  | HTML preparation | 2 | Compatibility testing
|  | HTML Validations | 3 | Deployment Documentation
|  | Web API Integration | 2
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Integration Testing | 1
|  | Total Time | 18
10 | Specific Article View | Low Level Design - Sequence Diagram | 3 | Integration Testing
|  | HTML preparation | 3 | Compatibility testing
|  | HTML Validations | 0.5 | Deployment Documentation
|  | Web API Integration | 2
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 3
|  | Code Cleanup | 1
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Integration Testing | 1
|  | Total Time | 21
11 | User Verification | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 4 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
|  | Web API Integration | 2
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 4
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Integration Testing | 1
|  | Total Time | 22
12 | Employees | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 4 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
|  | Web API Integration | 2
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 4
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Integration Testing | 1
|  | Total Time | 22
13 | Particular Article Review | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 5 | Compatibility testing
|  | HTML Validations | 2 | Deployment Documentation
|  | Web API Integration | 3
|  | Web API - Service Implementation | 4
|  | Swagger - API Documentation | 3
|  | Service Validations , Exception and Logging | 3
|  | Code Cleanup | 1
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Integration Testing | 1
|  | Total Time | 26.5
14 | To Review | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 3 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
|  | Web API Integration | 3
|  | Web API - Service Implementation | 4
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 3
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Integration Testing | 1
|  | Total Time | 22
15 | Reviewer Dashboard | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 3 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
|  | Web API Integration | 2
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Integration Testing | 1
|  | Total Time | 19
16 | Article Reviewed | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 2 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 3
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Integration Testing | 1
|  | Total Time | 17
17 | Latest Articles | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 3 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
|  | Web API Integration | 2
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 3
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Integration Testing | 1
|  | Total Time | 20
18 | Trending Articles | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 3 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
|  | Web API Integration | 2
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Integration Testing | 1
|  | Total Time | 19
19 | Latest Queries | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 3 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
|  | Web API Integration | 2
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Integration Testing | 1
|  | Total Time | 19
20 | Trending Queries | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 3 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
|  | Web API Integration | 2
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Integration Testing | 1
|  | Total Time | 19
21 | Articles | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 4 | Compatibility testing
|  | HTML Validations | 2 | Deployment Documentation
|  | Web API Integration | 2
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 3
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Integration Testing | 1
|  | Total Time | 22
22 | Queries | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 4 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Integration Testing | 1
|  | Total Time | 19
23 | My Articles | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 3 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Integration Testing | 1
|  | Total Time | 18
24 | My Queries | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 3 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
|  | Web API Integration | 2
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Integration Testing | 1
|  | Total Time | 19
25 | Create Article | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 4 | Compatibility testing
|  | HTML Validations | 2 | Deployment Documentation
|  | Web API Integration | 2
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Integration Testing | 1
|  | Total Time | 21.5
26 | Update Article | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 3 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
|  | Web API Integration | 2
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Integration Testing | 1
|  | Total Time | 19
27 | Specific Query View | Low Level Design - Sequence Diagram | 2 | Integration Testing
|  | HTML preparation | 3 | Compatibility testing
|  | HTML Validations | 0.5 | Deployment Documentation
|  | Web API Integration | 2
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
|  | Integration Testing | 1
|  | Total Time | 18.5
|  | TOTAL HOURS | 539