## Sheet1
Defect Id(Required) | Defect Title | Detailed Defect Description | Related Module/Component | Defect Status | Detected By | Assigneed To | Priority
1 | Register | Validation for email and password | Login | Closed | Girish | Sandhiya
2 | Validation | Validation for image | Create Article page | Closed | Sandhiya | Sandhiya
3 | Loading in homepage | Loading in homepage | Homepage | Open | Girish | Sandhiya | High
4 | No records found | Need to display no records found if no records to display | All pages | Closed | Girish | Sandhiya
5 | Comments | Comments bar in specific query and specific article boundary check | Specific article,Query | Closed | Sandhiya | Sandhiya
6 | Error messages | Add error and completed in all methods | All pages | Closed | Sandhiya | Girish
7 | Query filter | Query filter not working properly | Query filter | Closed | Girish | pooja
8 | Article filter | Article filter responsiveness | Article filter | Closed | Girish | pooja
9 | Data table | Data table not working properly | Data Table in admin pages | closed | Girish | Girish
10 | Comments | Commentsbox should be displayed only comment is there | Specific article,query | Closed | Girish | Irfan
11 | Button | Button in my queries should be aligned | My queries | Closed | Girish | Girish
12 | Login | Validation in Login | Login | Closed | Girish | Sandhiya
13 | ToReview page | To Review page not working correctly | ToReviewPage | Closed | Girish | Pooja
14 | Register | Totally needs to change | Register page | Closed | Prithivi | Sandhiya
15 | Readmore | If the content is less readmore goes top | articlecard,myarticle | open | Girish | Girish | Medium
16 | Article Filter | Have to reset date | Articlecard,myarticle | closed | Girish | Sandhiya
17 | Image in create article | Image is allowing pdf | Createarticle | closed | Sandhiya | Sandhiya
18 | Dashboard | Page is not responsive | Admin,reviewer dashboard | Closed | Girish | Sandhiya
19 | Breadcrumb | Have to check | all pages | Closed | Sandhiya | Girish
20 | Spamview | Boundarycheck | Spamview | Closed | Girish | Sriram
21 | Article filter | Alignment | Article filter | closed | Sandhiya | sandhiya
22 | Query filter | Alignment | Query filter | Closed | Sandhiya | Sriram
23 | Article filter | Date should be refreshed | Article filter | Closed | Girish | Sandhiya
24 | Myquery | Date should be refreshed | Query filter | Closed | Girish | Sandhiya
25 | Register | Fullname Length should be increased | Register page | Closed | Venkateshwaran | Sandhiya
26 | Register | ACE number length should be increased | Register page | Closed | Venkateshwaran | Sandhiya
27 | Register | Add Login page navigation link in register page. | Register page | Closed | Venkateshwaran | Sandhiya
28 | Rejection | Reason for rejection page needs breadcrum | Reason For Rejection Page | Closed | Venkateshwaran | Girish
29 | Rejection | Reason for rejection should not be empty. | Reason For Rejection Page | Closed | Venkateshwaran | Girish
30 | Employee | Disable user also have access to site. | Disable user | Closed | Venkateshwaran | Girish
31 | To reviewspecific page | Button in to review specific page is not alligned properly | ToReviewPage | Closed | Venkateshwaran | Girish
32 | Footer | In the footer email and details are underlined | Footer | Closed | Venkateshwaran | Girish
33 | To reviewspecific page | Reviewer can't see the image added in ck editor while reviewing Article | ToReviewPage | Closed | Venkateshwaran | Girish | High
34 | Login Page | user underverfication has access to home page. | Login Page | Closed | Mohammad Rafi | Girish
35 | To reviewspecific page | check in should be changed to checkout. | To Reviewspecific page | closed | Mohammad Rafi | Pooja
36 | To reviewspecific page | toast message in accept article. | To Reviewspecific page | Closed | Mohammad Rafi | Pooja
37 | Comments | Add Date and time of comment | Comments | Closed | Mohammad Rafi | Girish
38 | Register | Space between AlreadyRegister and Login | Register page | Closed | Mohammad Rafi | Pooja
39 | Spamview | reason for report F should be in Small. | Spamview | Closed | Mohammad Rafi | Irfan
40 | Spamview | date and time also in reason for spam. | Spamview | Closed | Mohammad Rafi | Irfan
41 | Comments | Logo and Name Needs Some Space. | Comments | Closed | Mohammad Rafi | Irfan
42 | Comments | post comment button should need space(Post) or change it to POST | Comments | Closed | Mohammad Rafi | Irfan
43 | Breadcrumb | Breadcrumb Needs to be corrected. | BreadCrumb | Closed | Mohammad Rafi | pooja/irfan | Medium
44 | All Page | Font in footer and header should be same | All pages | Closed | Mohammad Rafi | Girish
45 | Queries | Radio button is too close to label | Queries | Closed | Mohammad Rafi | Pooja
46 | Queries | Search and textbox is too close | Queries | Closed | Mohammad Rafi | Pooja
47 | Employee Details | Employee table header and search are too close. | Employee Details | Open | Mohammad Rafi | Due to datatable cannot do anything | Low
48 | General | Avoid Camel Case | General | Closed | Mohammad Rafi | Pooja
49 | Spamview | Remove Query Button Not Working | Spamview | Closed | Venkateshwaran | Girish
50 | Query page | While we are searching a query pagination error | Query Page | Open | Venkateshwaran | Girish | low | Due to glitch
51 | Private Article | Private Article is shown to the specific user even it is not reviewed. | Private Article | Closed | Venkateshwaran | Manimaran | High
52 | Myquery | Query is visible to the specific user even it is marked as spam and removed. | My queries | Closed | Venkateshwaran | Girish | Medium
53 | Article filter | Upto today's date should be shown ( User can't able to tomorrow's date for search | Article filter | Open | Venkateshwaran | Girish | Low
54 | Reviewer Dashboard | Pie Chart color and Hover color is not same | Reviewer Dashboard | Closed | Venkateshwaran | Pooja | Medium
55 | Update Article | Reason rejection box should contains text limit | Update Article | Closed | Venkateshwaran | Girish | Medium
56 | Create article | Ck editor Spell Checker not working. | Create Article | Open | Venkateshwaran | Girish | High
57 | Specific Article | Toast Message is also appear when there is no content available. | Specific article | Closed | Venkateshwaran | Girish | Low
58 | Specific Article | Comment Function not working | Specific article | Closed | Girish | Manimaran
59 | Specific Query | Comment Function not working | Specific Query | Closed | Girish | Manimaran
60 | Specific Article | Read More Button to be shown | Specific article | Closed | Venkateshwaran | Sandhiya
61 | Reviewer Dashboard | Change the name of Article reviewed | Reviewer Dashboard | Closed | Venkateshwaran | Girish | Medium
62 | My Query Specific | Footer is unstable while there is no comments/answers for it | MyQuery Specific | Closed | Venkateshwaran | Girish
63 | Raisequery | Query Code having default 200 words limit | RaiseQuery | Closed | Venkateshwaran | Girish
64 | Myarticle | Date is not showing properly | MyArticle | Closed | Venkateshwaran | Girish
65 | Specific Query | Comments also need code allignment function | Specific Query | Open | Venkateshwaran | Girish
66
67
68
69
70
71
1 | Login | done
2 | Register | done
3 | Home | done
4 | View Article | done
5 | Articlefilter | done
6 | QueryFilter | done
7 | View Query | done
8 | Myarticle | done
9 | Editarticle | done
10 | Myquery | done
11 | Private Article | done
12 | View profile | done
13 | Create article | done
14 | Raisequery | done
15 | To reviewspecific page | done
16 | To review | done
17 | ArticleReviewed | done
18 | Articlereviwedspecific | done
19 | Reason for article if rejected | done
20 | Userverification | done
21 | Employee | done