## Template
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Girishkumar
Gowtham
Mani Maran
Mohammed Irfan
Ponvizhi
Pooja
Ranjith
Sandhiya
Sriram
Venkateshwaran

## 05.04.2022
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Venkateshwaran | Individual Admin and Reviewer Flow | Created User stories for individual actors |  | 6 | 1
Mani Maran | Individual Admin and Reviewer Flow | Created User stories for individual actors |  | 6 | 1
Ponvizhi | Individual Query Solver and Query Raiser | Created User stories for individual actors |  | 6 | 1
Mohammed Irfan | Individual Query Solver and Query Raiser | Created User stories for individual actors |  | 6 | 1
Sandhiya | Creation of User Flow,Admin flow | Created User stories for individual actors |  | 6 | 1
Pooja | Creation of User Flow,Admin flow | Created User stories for individual actors |  | 6 | 1
Ranjith | Absent | Created User stories for individual actors | Absent | Absent | Absent
Sriram | Absent | Created User stories for individual actors | Absent | Absent | Absent
Gowtham | Absent | Created User stories for individual actors | Absent | Absent | Absent
Girishkumar | Creation of User Flow,Admin flow | Created User stories for individual actors |  | 6 | 1

## 06.04.2022
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Girishkumar | Refining of Admin flow,and started with creating wireframe for forum | Created admin flow and refined the user stories |  | 6 | 1
Gowtham | Discuss about user flow and create user flow diagram.create wire frame for admin side -reviewer &user verification view. | Absent |  | 5 | 1
Mani Maran | Refining of Individual Admin flow and Reviewer flow,refined in Actor flow docs and started with creating wireframe for Admin Dashboard page. | Created Individual admin and Reviewer flow,Added MOM in excel |  | 5 | 2
Mohammed Irfan | Refining of Query solving and Query Raising flow.Created Wireframe for Reviewing page. | Created User stories for individual actors,Added Query raiser and query solver in excel. |  | 5 | 2
Ponvizhi | Refining User Flow of Query solving and Query Raising .Created Wireframe for Reviewer Dashboard. | Created User stories for individual actors,Added Query raiser and query solver in excel. |  | 5.5 | 1
Pooja | Refined the User flow according to the suggestions given and wireframe for articless . | Created User Flow,User stories for Article publisher and reader has been refined |  | 6 | 1
Ranjith | Absent | Absent | Absent | Absent | Absent
Sandhiya | Creation of Reviewer flow and started creating wireframe for home page,profile page ,article page. | Created User flow and admin flow and refined user stories for author |  | 6 | 1
Sriram | Refining the queryraiser and query solver.Created wireframework for login and register | Absent |  | 6 | 1
Venkateshwaran | Refining of the reviewer flow,Started Creating the wireframe for spam query report and user authorization | Created Individual user flow and refined with the user stories |  | 5 | 2

## 07.04.2022
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Girishkumar | Created Wireframes for forum page,query raising page,report query page and view query page. | Refined the Admin flow and started planning wireframes for forum |  | 6 | 1
Gowtham | created wire frame for admin side -reviewer &user verification view. | Discuss about user flow and create user flow diagram.Planning wire frame for admin side -reviewer &user verification view.
Mani Maran | Created Wireframe for Admin Dashboard overview page,Employees page . | I wrote Acceptance Criteria,Dependencies,constraints for Article reviewer |  | 2,1.5,1.5,1 | 2
Mohammed Irfan | Created wireframe for Reviewer page,publish and report page. | Refined query solver,query raiser flow and discuss with team about wireframe. |  | 6 | 1
Ponvizhi | Created wireframe for Reviewer Dashboard.Acceptance criteria for Query Solver. | Refining query solver , query raiser and created wireframe for reviewer dashboard. |  | 6 | 1.5
Pooja | The wireframe for Myarticles,Published articles and Draft has been created | The User flow has been refined and the wireframe for Myarticles has been planned |  | 7 | 1
Ranjith
Sandhiya | Created HomePage,Profile and article page | Refined Review flow and started with planning Wireframe for Home ,Profile and article page. |  | 6 | 1.5
Sriram | Creating Login and Register page. Acceptance criteria for Query Raiser | Refined query raiser flow and started planning wireframe for Login,Register page. |  | 6 | 1
Venkateshwaran | Created wrieframe for spamreports | I have created acceptance criteria , dependencies,constraints for Admin |  | 1.5,1.5,1.5,1 | 3

## 08.04.2022
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Girishkumar | Refined the wireframes of forum module like adding query page,Viewing specific query page and commenting to the query and search query | Created wireframes for forum pages like query viewing,adding quering,reporting spam |  | 6 | 2
Gowtham | Refined the wireframes of admin page and created entity model | created wire frame for admin side -reviewer &user verification view. |  | 5 | 1
Mani Maran
Mohammed Irfan | Work on entity model on Reviewer Dashboard. | Redefined Wireframe for Reviewer Dashboard,Publish and Reject Page. |  | 6 | 2
Ponvizhi |  | Created wireframe for Reviewer Dashboard |  | 6 | 2
Pooja | Refined the WireFrames for Published Articles,Draft and Worked on entity model | Created the wireframes for My Articles page,Published and Draft page and Create Articles Page |  | 3,1,1 | 2
Ranjith
Sandhiya | Refined the wireframe for homepage, article page and added pagenation and worked on entity model | Created wireframe for homepage and article page |  | 6 | 1.5
Sriram | Refined the wieframe for Login and register page and worked on entity model on query raiser | Created wireframe for login and register |  | 6 | 2
Venkateshwaran | Working on entity model | Refined the wireframe Spam query list and reported query list |  | 1,1,1 | 2,1,1,1,1

## 09.04.2022
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Girishkumar
Gowtham | Refining Admin page and worked on entity model | created wire frame for admin side -reviewer &user verification view
Mani Maran
Mohammed Irfan | Work on entity model. | Refined the wireframe for Reviewer dashboard,Review page and Publish page |  | 6 | 1
Ponvizhi
Pooja | Refined The Wireframes based on the suggestions given, and Worked on Entity Models | Refined the WireFrames for Published Articles,Draft and Worked on entity model |  | 2,1.5,2 | 1
Ranjith
Sandhiya | Refined the wireframe for homepage,articlepage and worked on entity models | Refined the wireframe for homepage,profile page and article page |  | 6 | 1
Sriram | Refined made on login and register wireframe and worked on entity model on query | Changes made on entity model and wireframe |  | 6 | 1
Venkateshwaran | Worked on Entity Models and Refining the wireframes | Refined wireframes on spam report list |  | 2,2,1 | 2

## 11.04.2022
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Girishkumar | Refined the Wireframes of Forum pages Like Adding query pageand viewing query page,Discussed about the data model entities and created the data model | Made the changes in the forum wireframe. Explored on data model and DBcontext |  | 6 | 1
Gowtham | Refined Admin wireframe.Discussing about Entity Data Model.Started designing Data model | Made the changes in the admin wireframe |  | 6 | 1
Mani Maran | 1.Refining Admin Dashboard Wireframe. 2.Discussing about Entity Data Model. 3.Started designing Data model | Completed Changes in Wireframe. Explored about Middlewares and Pipelines |  | 2 1 2 | 1.5
Mohammed Irfan | Refined Reviwer Dashboard,Reviewer page,Publish page and Discussed the data models. | Refined the Changes in Wireframe(Reviewer flow). |  | 5 | 1
Ponvizhi | Refined Reviewer Dashboard and Dissued Data Models and created data models | Refined the changes in reviewer dashboard |  | 5 | 1
Pooja | Refined the Wireframes of Articles Page, Created MOM, Discussed the Data Models and created data models | Refined the changes in the Articles and forum Page.Explored on EAR |  | 5 | 1
Ranjith
Sandhiya | Refined Article Page ,Created Data Model with example | Refined Changes in Home Page,discussed and created DataModel |  | 5 | 1
Sriram | Refining the data model for query table | Updated wireframe for login and register
Venkateshwaran | Discussed Data Models and created data models | Refined Spam report wireframe |  | 4 | 2

## 12.04.2022
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Girishkumar | 1.Working on physical model,convert of conceptual model to physical model 2.refrained the changes of the filter in the wireframes | Brainstorming- 1hr Discussion about Data model-1hr Creation of user entity in Data model -1.30hr Refrained the data model -2hr Review Session with Rafi-1hr Discussed about the Changes need to done after Review -1hr Explored About Code First and DB first Approach-1hr |  | 7.30 hours | 1hour
Gowtham | created Logical data model with operations | Refined Admin wireframe.Discussing about Entity Data Model.Started designing Data model |  | 6:00Hour | 1Hour
Mani Maran | 1.Working on Logical and physical model. 2.Operations in Datamodel. | Discussion about DataModel - 1hr Createddatamodel for Article,Article-Comment,Article-Rating - 2hr Mapped relationships between data models - 1.5hr Review Session with Rafi-1hr Team Retrospecive meeting -1hr Explored about Context classes in Entity Core - 1hr |  | 6.30 hours | 1 hour
Mohammed Irfan | Working on Operation in datamodel and Physical model. | Datamodel(Discussion) - 1 hr Creation of entity data model - 2 hrs Refined the Data model- 1 hr Session with Rafi - 1 hr Team discussion (After Review ) - 1 hr |  | 6:00 hours | 2 hours
Ponvizhi | Created data models and relationship. | Refined wireframe for reviewer dashboard. |  | 7:00 hours | 1 hour
Pooja | Worked on the convertion of conceptual model to logical model. | Brain stroming -1hr Discussed about data model -1 hr Creation of Data table and check the data model flow -2 hr refined the Data Model -1 hr Session with Rafi - 1 hr Team discussion on the changes to be done after meeting -1 hr |  | 7:00 hours | 2 hours
Ranjith
Sandhiya | working on logical model and physical model and operations. | Brainstorming- 1hr Discussion about Data model-1hr Creation of article entity in Data model -1.30hr Refined the data model -1hr Review Session with Rafi-1hr Discussed about the Changes need to done after Review -1hr |  | 6.30 hrs | 1Hour
Sriram | Identified operation for the entity in conceptual model | Brainstorming- 1hr Discussion about Data model-1hr Creation of Query entity in Data model -1.30hr Refined the data model -2hr Review Session with Rafi-1hr Discussed about the Changes need to done after Review -1hr |  | 7.30 hours | 1 hour
Venkateshwaran | Working on Refining User Stories | Discussed about data model -1 hr Creation of Data table and check the data model flow -1 hr 15 mins Refined the Data Model -45 mins Review Session with Rafi - 1 hr Team discussion on the changes to be done after meeting -1 hr |  | 5:00 hours | 2:00 hours

## 13.04.2022
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Girishkumar | Explored about the HLD Document, Started Creating HLD | 1.Creation of Physical model and logical model-2hr 2.Discussion with Rafi-30mins 3.Refined the wireframes of the filter in the user side-2hr 4.Explored on middlewares and pipeline-1.30 |  | 5.30 hours | 1.30 hours
Gowtham | Explored on Html,css and started creating layout | Created the operation for data model |  | 5 | 2
Mani Maran | 1.Refining Operations in Data Model. 2.High Level Design | 1. Started Creating operations in Data Model - 2hr 2.Group Dicussion for creating Physical and logical model -1hr 3.Meeting With Raffi regarding HLD - 1hr 4.Explored about High Level Design - 1hr 5.Explored about Entity Db Context class -1 hr |  | 6hours | 2 hour
Mohammed Irfan | Start working on Layout. | Worked on datamodel(Logical). |  | 6 | 2
Ponvizhi | Added Operations for data model and converted into physical model | finished Physical data model |  | 6 | 1
Pooja | Started creating HLD | Creation of Logical model meeting with Rafi Explored on HLD |  | 5 | 1
Ranjith
Sandhiya | Explored on Html,css and started layout | worked on physical and logical model |  | 5 | 1
Sriram | Creating the operation for data model | Discussed about the Changes need to done after Review Refined the data model Discussion with Raffi about design pattern |  | 5 hours | 2 hours
Venkateshwaran | Refining the acceptance criteria,dependencies,constraints | Group Dicussion for creating Physical and logical model -1hour Meeting With Raffi regarding HLD - 1hour Explored about High Level Design - 30 Mins |  | 4:30 Hours | 2:00 hours

## 18.04.2022
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Girishkumar | Working on HLD Document | Refining of Physical model and Logical model-1hr Explored about the HLD Document and worked on the HLD Document -2hr Explored on Code first Approach in the Web API-2hr Explored about the HTTP Verbs and methods in the Web API-2hr |  | 3 Hours | 4 Hours
Gowtham | Working on Home layout | Created the operation for data model-1hr.Explored angular-3hr |  | 3 Hours | 3 Hours
Mani Maran | Refining ViewModel and Operations in Datamodel . | Refined Datamodel operations . started creating view models. Explored and worked with Web Api Scaffold,Code First and Database First Approach using migrations in Sample Application. Explored about typescript. |  | 4 hours | 2.5 hours
Mohammed Irfan | Working on HTML Layout. | Refined Data model operations. Learned Codefirst approach and Angular . |  | 6 | 2
Ponvizhi | Working on HLD Document | Refined operations on the data model. Explored about creating web api , angular and typescript. |  | 6 | 1
Pooja | Working on HLD Document | Refined the physical model Explored on HLD,Web API,Typescript |  | 4 hours | 2
Ranjith
Sandhiya | Working on Layout | Explored on code first Approach and Angular-2hr. Started Creating layout-2hr |  | 4hrs | 2
Sriram | Working on operation in the data model | Refining the operation on the data model. Exploring about the code first approach |  | 5 hours | 1 hour
Venkateshwaran | Refining ViewModel and Operations. | Refined the acceptance criteria,dependencies,constraints |  | 5:00 hours | 2:00 hours

## 19.04.2022
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Girishkumar | Working on the HLD Document, and created Layout for the user side | Explored About components and System architecture for the HLD document Started Working on the HLD document Explored about the Components in Angular |  | 6 | 2
Gowtham | Created layout for user footer | Explored about Angular Explored about TypeScript |  | 6 | 2
Mani Maran | Refining in View Model | Refined View Model and Operations in DataModel.2h Started Exploring about Angular and its components. 1.5hr Created Sample Component and Worked with Sample API in Angular. 2hr Explored about typecript.1hr |  | 5 hours | 2 hours
Mohammed Irfan | Working on Admin Layout. | Explored on Typescript. Worked on Admin side layout. |  | 5 hrs | 3 hrs
Ponvizhi | Working on View Model | Explored on Typescript. Worked on Dashboard for Layouts. |  | 5 | 3
Pooja | Working on the HLD document. | Explored on Components and system Architecture Created the Database Dictionary Started working on HLD |  | 5 | 2
Ranjith | Working on layout | explored concepts on type script .working on layout |  | 5 hrs | 2 hrs
Sandhiya | Created layout for user navigation bar | Explored on Typescript and component files in angular. Worked on user side layout. |  | 5 | 3
Sriram | Worked on view model | Explored about Typescript and worked on sample code. Refining operation in the data model. |  | 5 | 2
Venkateshwaran | Exploring on dashboard layout | Started Exploring about typescripts Refined the view model and operations |  | 3 | 5

## 20.04.2022
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Girishkumar | Working on the Layout of user side | 1.Session on Design pattern -1hr 2.Session on HLD -30mins 3.Review Session with Rafi -30mins 4.Refined the Data model -1hr 5.Refined the operation and added input,output in the data model-1.30mins 6.Worked on the Main layout page for the userside-2hr 7.Explored on the angular component(html template,component class,component metadata)-1.30hr |  | 6.30hours | 1.30hours
Gowtham | Working on System Architecture | Worked on System Architecture -1hr Attended Rafi session -30min Review with Rafi -30min Softskill Training-1hr |  | 3hr | 1hr
Mani Maran | Refining Services in Class File | 1.Refined Viewmodel and operations -2hr 2.Session on HLD - 30min 3. Created Article Card Component in Angular-1hr, 4.SoftSkill session-1hr, 5.Started creating services for datamodel. -1hr 6.Worked with sample Web ApI -1hr 7.Review meeting with Raffi -30min |  | 6hour | 1hour
Mohammed Irfan | Working on Dependencies Interactions. | Softskill session - 1hr Session on HLD - 30mins Explored angular concept - 2hr Worked on Admin Dashboard Layout - 2 hrs Team Discussion - 30mins Review meeting - 30mins |  | 5 hrs | 1 hr 30 min
Ponvizhi | Working on Services | Refined ViewModel Softskill Session Session on HLD |  | 5 | 2
Pooja | Working on Data model and Services | SoftSkill Session Session on High level design with Rafi Review Session with Rafi Started working on the Refining of operations in Datamodel |  | 5 hrs | 1
Ranjith | Working on NFR | Worked on Review Dashboard Layout Team Discussion Review meeting SoftSkill session-1hr, Session on HLD - 3O mins Exploring angular |  | 5hr | 1 hr
Sandhiya | Working on System Architecture | Worked on Navigation bar for user side-1.30hr Attended rafi session about hld-30mins Review with rafi-30mins Worked on System Architecture-1hr Explored on Src files,types of binding in angular and typescript-2.30hrs soft skill-1hr |  | 3.3hrs | 3.3hrs
Sriram | Working on system architecture and NFR | Attended soft skill session-1hr Attended the session on Hld-30min Review session with raffi-30min Worked on System Architecture-1hr Worked on NFR-1hr Working on uer side layout-1hr |  | 4 hrs | 2 hrs
Venkateshwaran | Working on Database Diagram | 1Session on HLD with Rafi -40mins 2.Project Review Session with Rafi -32mins 3.Softskill Sessions - 1hr |  | 4hours 30Mintues | 3 hours

## 21.04.2022
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Girishkumar | Working on the Editor in the Create article page | 9.00-9.15 -Brainstorming with team 9.15-10.15-Refined the Articles,Articles Comment,user,department and designation entity 10.15-10.40-Break 10.40-12.00-Refined the operation for article,article comment,user,department and designation entity 12.00-12.30-Referring other team mates work 12.30-1.00-Discussion with the team before meeting 1.00-1.30-Lunch 1.30-2.45-Review session with rafi 3.00-4.00-Timesheet and SVN Session by AspireSystems 4.00-4.30-Break 4.30-5.00-Discussion with team after the review meeting 5.00-6.00-Started working on the editor in the create article page |  | 6.20 hours | 2.25 hours
Gowtham | Creating system architecture | 9.00-9.15 -Team discussion 9.30-10.30-Discussed about creating System Architecture 10.30-10.45-break 10.45-11.30-Created System Architecture 11.30-12.30-Explored basic concept of type script and worked on data types 12.30-1.00-Discussion with the team before meeting 1.00-1.30-Lunch 1.30-2.45-Review session with rafi 3.00-4.00-Timesheet and SVN Session by AspireSystems 4.00-4.20-Break 4.30-5.00-Discussion with team after the review meeting 5.00-6.00-Explored System Architecture(presentation layer,bussiness layer,data access layer & cross cutting concerns) |  | 6.45 hr | 2.15
Mani Maran | Creating Sample Web API | 9.00 - 9.15 -General Discussion 9.15-10.00-Refined Operations in the data model 10.00-11.00 - created Services and its methods. 11.00-11.20 - Coffee break 11.20-12.00 - Refined Services 12.00-12.30 - Refined database diagram in SQL 12.30-1.00 - Team Discussion before review 1.00-1.30 - Lunch 1.30-2.45 - Review Meeting with Raffi 3.00-4.00 -Timesheet and SVN session by AspireSystems 4.00-4.20 - Break 4.30-5.00-Team Discussion After Review 5.00-6.00 - Worked with Sample Web API.S |  | 6.15hour | 2 hour
Mohammed Irfan | Worked on Dependency. | 9.00-9.15 -Brainstorming with team 9.15-10.30-Worked on Services and Dependency Interaction. 10.30-10.40-Break 10.40-12.30-Learned AngularMaterial,DesignComponent,Route modules,created sample dashboard and How to import Api in src file. 12.30-1.00-Discussion with the team before meeting 1.00-1.30-Break 1.30-2.45-Review session with rafi 3.00-4.00-Timesheet and SVN Session by AspireSystems 4.00-4.30-Break 4.30-5.00-Discussion with team after the review meeting 5.00-5.45-Refined MasterTable services and discuss with team. |  | 6.hours | 2.10hours
Ponvizhi | Working on Services | 9.00-9.15 -Brainstorming with team. 9:40-11:10 - Worked on services. 12.30-1.00-Discussion with the team before meeting. 1.00-1.30-Lunch. 1.30-2.45-Review session with rafi. 3.00-4.00-Timesheet and SVN Session by AspireSystems . 4.30-5.00-Discussion with team after the review meeting . 5.10-5.30- Gathering information to do sample web api. |  | 4 | 2
Pooja | Working on services | BrainStroming with Team -9.00-9.15 Worked on refining the operations of Query,QueryComment,Spam,VerifyStatus -9.30 - 12.00 Discussion with Team before Review -12.30 -1.00 Lunch -1.00 -1.25 Session with Rafi -1.30 -2.45 Attended Timesheet and SVN session by AspireSystems -3.00 -4.00 Discussion with the team about review meeting -4.30 -5.00 Created the Master Table services -5.00 -5.15 Refined the Article and User Services -5.15 -5.40 Changes in the Services has been done with discussion -5.40 -6.00 |  | 5 hours | 1 hour
Ranjith | Working on NFR | 9.00-9.15 -Brainstorming with team 9.30-10.30-NFR 10.30-10.45-break 10.45-12.00-In Angular(commands) worked on sample codes 12.00-12.30-learnt about HTTP(put,update,delete,get) 12.30-1.00-Discussion with the team before meeting 1.00-1.30-Lunch 1.30-2.45-Review session with rafi 3.00-4.00-Timesheet and SVN Session by AspireSystems4.00-4.30 -Break 4.30-5.00-Discussion with team after the review meeting 5.00-5.30-Data model |  | 5 hours | 2 hours
Sandhiya | Working On Article Side Layout | 9.00-9.15 Brainstroming 9.15-10.30 Designed User Layout 10.30-10-45 Break 10.45-11.15 System Architecture 11.15-12.30 Worked on typescript(class,function,array) and angular(interpolation,property) 12.30-1.00 Discussion with team 1.00-1.30 Lunch 1.30-2.45 Review with Rafi 2.45-3.00 break 3.00-4.00 Timesheet and SNS Session by AspireSystems 4.00-4.30 Break 4.30-5.00 Discussion with team 5.00-5.50 Worked on basic code of WebApi CodeFirst approach |  | 5hrs | 2hrs 20 mins
Sriram | working on bread crums and pagination | 9.00am-9.15am Brainstroming with team 9.15am-9.20am Mail checking 9.20am-10.25am Working on system architecture 10.25am-11.00am Working on NFR 11.00am-11.20am Tea break 11.20am-12.30pm Understanding the service,database diagram,data model done by the organization. 12.30pm-1.15pm Lunch 1.30pm-2.45pm review seesion with Rafi 3.00pm-4.00pm Timesheet and SVN session by AspireSystems 4.00pm-4.30pm Tea break 4.30pm-5.00pm discussion about the work split in team |  | 3.55 Hours | 2.35 Hours
Venkateshwaran | Refineing system architecture | 9.00-9.15 -Brainstorming with team 9.15-10.30-Database Diagram 10.30-11:00-Break 11.00-12.00-Reviewing and Correcting the database Diagram. 12.30-1.00-Discussion with the team before meeting 1.00-1.30-Lunch 1.30-2.45-Review session with rafi 3.00-4.00-Timesheet and SVN Session by AspireSystems 4.00-4.30-Break 4.30-5.00-Discussion with team after the review meeting and splited the work. 5.00-5:30 - Had a look on system architecture concepts. |  | 4hrs 30 mins | 3 hrs

## 22.04.2022
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Girishkumar | Working on the editor,cards view and filter | 9.00-9.15 -Brainstorming with team 9.15-10.15-Searched for the Text editor template and tried out the samples to include in the application 10.15-10.40-Break 11.00-12.00-Refined the navigation bar and footer in the user side layout 12.00-12.30-Reviewed and referred teammates work 12.30-1.00-Discussion with team before meeting 1.00-1.50-Lunch 2.00-3.05-Review Session with Rafi 3.10-3.30-Discussion with team after the review 3.30-5.00-Activity session with Training department 5.00.5.30-Tea Break 5.30-6.00-Discussion with team after the review |  | 5.10 hours | 3.15 hrs
Gowtham | creating interaction | 9.00-9.15 -Team discussion 9.30-10.30- created System Architecture 10.30-10.45-break 11.00-12.30- type script - worked on(variables,operators,decision making) 12.30-1.00-Discussion with the team before meeting 1.00-2.00-Lunch 2.00-3.05-Review session with rafi 3.10-3.30-Discussion with team after the review 3.30-5.00-Activity session with Training department 5.00-5.30-Break 5.30-6.00-Discussion with team after the review |  | 6hr | 3hr
Mani Maran | Working on web api | 9.00-9.15 -Team discussion 9.30-10.30- explored on web api 10.30-10.45-break 11.00-12.30-worked on web api and refine the services 12.30-1.00-Discussion with the team before meeting 1.00-2.00-Lunch 2.00-3.05-Review session with rafi 3.10-3.30-Discussion with team after the review 3.30-5.00-Activity session with Training department 5.00-5.30-Break 5.30-6.00-Discussion with team after the review |  | 5 | 2
Mohammed Irfan | Working on admin dashboard | 09.00-09.15- Brainstroming with team 09.15-11.00-Learned Angular Concept(Api,routing modules) 11.00-11.20-Break 11.20-12.30-Working on Admin Dashboard 12.30-01.00- Discusion with team 01.00-02.00- Break 02.00-03.05-Review session with Rafi 03.05-03.30-Discussion with team 03.30-05.00-Activity session with Training team 05.00-05.30-Working on Admin Dashboard 05.30-06.00-Discussion with team. |  | 5 | 3
Ponvizhi | Working on web api | 09.00-09.15- Brainstroming with team 09.15-11.00-Learned Angular Concept 11.00-11.20-Break 11.20-12.30-Working on web api sample 12.30-01.00- Discusion with team 01.00-02.00- Break 02.00-03.05-Review session with Rafi 03.05-03.30-Discussion with team 03.30-05.00-Activity session with Training team 05.00-05.30-NFR 05.30-06.00-Discussion with team. |  | 4 | 3
Pooja | Working on the Refining of DataModel,Services for the Spam and Reviewer | 9.00-9.30 Brainstroming with the Team 9.30-10.30 Refined the services of Article and Query Services 10.45-11.00 Break 11.00-12.15 Review the Services and made changes in the services 12.00-12.30 Understand the works done by the team members 12.30-1.00 Team Discussion before review 1.00-1.45 Lunch 2.00-3.05 Session with Rafi 3.10-3.25 Discussion with team After review 3.30-5.00 Fun Friday Activity 5.00 -5.25 Break 5.30-6.00 Team discussion aboutthe review meeting and works to be done |  | 5 hours | 1.30 hours
Ranjith | Working on admin dashboard | 9.00-9.15 - Brainstroming 9.30-11.00-Anguar(routing, module,components(html,css)) 10.30-11.00 -Break 11.00-12.30 - Worked on Reviewer Dashboard 12.30-1.00 Team Discussion 1.00-1.55 Lunch 2.00-3.05 Review session with rafi 3.10-3.30 Discussion with team 3.30-5.00 Activity with Training department 5.00-5.30 Break 5.30-6.00 Discussion with team |  | 5.30 hr | 2 hr
Sandhiya | Craetaing a layout page for particular query | 9.00-9.15 Brainstroming 9.15-10.30 Worked on cards in User side 10.30-11.00 Break 11.00-12.15 Worked on Full Page Alignment for user side. 12.15-12.30 Discussed on Services 12.30-1.00 Team Discussion 1.00-1.55 Lunch 2.00-3.05 Review session with rafi 3.10-3.30 Discussion with team 3.30-5.00 Activity with Training department 5.00-5.30 Break 5.30-6.00 Discussion with team |  | 5hrs | 1hr 30 mins
Sriram | Creating a layout page for particular article | 9.00-9.15- Brainstroming with team 9.15-11.00-working on layout on home page 11.00-11.20-Break 11.20-12.30-working on Home page 12.30-1.00- discusion with team 1.00-2.00- Lunch 2.00-3.05-Review session with Rafi 3.05-3.30-Discussion with team 3.30-5.00-Activity session with training team 5.00-5.30-Tea break 5.30-6.00-Discussion with team |  | 4 | 3
Venkateshwaran | Working on web api | 9.00-9.15- Brainstroming with team 9.15-11.00-Reviewing services 11.00-11.40-Break 11.40-12.30-Reviewing NFR 12.30-1.00- Discusion with team 1.00-2.00- Lunch 2.00-3.05-Review session with Rafi (43Mins) 3.05-3.30-Discussion with Team 3.30-5.00-Activity session with training team 5.00-5.30-coffee break 5.30-6.00-Discussion with team |  | 3:30 | 5:00

## 23.04.2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Girishkumar | Working on User Side Article and Query Cards | Absent |  | 3 | 5
Gowtham | Absent | 09.00-09.15- Brainstroming with team 09.15-11.00-Worked on Interaction . 11.00-11.20-Break 11.20-01.00-Worked on Interaction. 01.00-02.00- Break 02.00-02.30- Discussion with team 02.30-03.20-Review session with Rafi 03.20-03.50-Discussion with team 03.50-04.10-Break |  | 4.5 | 2
Mani Maran | Working on sample WebApi | Absent |  | 2 | 6
Mohammed Irfan | Working on Admin and Reviewer works. | 09.00-09.15- Brainstroming with team 09.15-11.00-Worked on Admin Dashboard. 11.00-11.20-Break 11.20-01.00-Worked on Admin Dashboard 01.00-02.00- Break 02.00-02.30- Discussion with team 02.30-03.20-Review session with Rafi 03.20-03.50-Discussion with team 03.50-04.10-Break 04.10-05.30-Working on Reviewer Dashboard |  | 5.30 hrs | 1.50hr
Ponvizhi | Working on web api | Absent |  | 4 | 3
Pooja | Working on Admin Layout | 9.00-9.15 Brainstroming with the Team 9.45-10.30 Worked on Refining the datamodel and services 10.20-11.10 Discussion about the changes to be made in Spam Report 11.20-11.35 Break 12.00-12.30 Modified the changes in the datamodel after discussion 12.30-1.00 Team Discussion before review 1.00-1.45 Worked on Dependencies 2.05-2.25 Lunch 2.30-3.20 Session with Rafi 3.30-3.50 Break 4.00-5.00 Team discussion about the review meeting and changes to be done |  | 5 | 1
Ranjith | Working on review(content) dashboard | 09.00-09.15- Brainstroming with team 09.15-11.00-Worked on Reviewer (content) Dashboard. 11.00-11.30-Break 11.30-01.00-Worked on Review side (To Review) 01.00-02.00- Break 02.00-02.30- Discussion with team 02.30-03.20-Review session with Rafi 03.20-03.50-Discussion with team 03.50-04.20-Break 04.20-05.30-Working on Reviewer side (Article Reviewed) |  | 6 hr | 2 hr
Sandhiya |  | 9.00-9.15 Brainstroming with team 9.15-10 Worked on interactions and Query Layout 10-10.40 Discussed on Query Services with team 10.40-11 Break 11-1 Worked on User Side 1-2 Lunch 2.30-3.20 Session with Rafi 3.20-3.30 break 3.35-4 Worked on User side 4.00-5.00 Discussion with team |  | 6hr 30mins | 1hr
Sriram |  | 9.00-9.15 Brainstroming with team 9.15-10.20 Worked on the particular article 10.20-11.10 Discussion about the changes in the spam report 11.10-11.35 Break 11.35-12.30 worked on the article pag 12.30-1.00 Discussion with team 1.00-1.45 Lunch 2.30-3.20 Review session 3.20-3.50 Break 3.50-4.30 team discussion 4.30-5.20 worked o the layout
Venkateshwaran | Working on spam reports layout | 9.00-9.30 Brainstroming with the Team 9.45-10.30 Worked on Refining the datamodel and services 10.20-11.10 Discussion about the changes to be made in Spam Report 11.20-11.35 Break 12.30-1.00 Team Discussion before review 1.00-1.45 Worked on Dependencies 2.05-2.25 Lunch 2.30-3.20 Session with Rafi 3.30-3.50 Break 4.00-5.00 Team discussion about the review meeting and changes to be done